## Env't & Green Spaces Group
Project Plan for West Wittering Neighbourhood Plan
|  | Completed |  |  |  | In Progress |  |  |  |  | Not yet started
|  | 2016 | 2017 | [11 empty] | 2018
Lead | Key Activity | >Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Inception (Evidence Gathering & Commnity Engagement)
SG start up and formation | bar: 2016 >Dec
NDP Launch and open day | bar: 2016 >Dec
Focus Groups set up | bar: 2016 >Dec to 2017 Feb
Ongoing engagement & evidence gathering | bar: 2017 Jan to 2017 Jun
Survey work (NDP, Housing Needs)
Engage with Businesses, YP, Organisations
Review VDS and amend | bar: 2017 Jan to 2017 May
Idenity Heritage and Community Assets | bar: 2017 Mar to 2017 May
Scoping Report Consultation | bar: 2017 Mar to 2017 May
Carry out a Tourism survey | bar: 2017 Mar to 2017 May
Engage with landowners (call for sites) | bar: 2017 Mar to 2017 May
Assess sites and write report | bar: 2017 May to 2017 Aug
Identify and Allocate Local green Spaces | bar: 2017 Jun to 2017 Aug
Draft Plan & Regulation 14
Prepare draft plan and draft SEA | bar: 2017 Aug to 2017 sep
Carry out Regulation 14 | bar: 2017 sep to 2017 Oct
Log and comment on representations | bar: 2017 Oct to 2017 Nov
Meet with LPA | bar: 2017 Nov
Finalise Consultation Statement | bar: 2017 Nov
Submission Plan & Regulatin 16
Amend plan and SEA with comments | bar: 2017 Nov to 2018 Jan
Write Basic Conditions Statement | bar: 2017 Nov to 2018 Jan
SG approve and submit plan and associated documents to PC | bar: 2018 Jan to 2018 Feb
PC submit plan and associated docs to LPA | bar: 2018 Jan to 2018 Feb
| SG - steering group | 2016 >Dec: PC - Parish Council; 2017 Jul: LPA - Local Planning Authority
| YP - Young People | 2016 >Dec: VDS - Village Design Statement