## Env't & Green Spaces Group
Project Plan for West Wittering Neighbourhood Plan - June 2017
|  | Completed |  |  |  | In Progress |  |  |  |  | Not yet started
|  | 2016 | 2017 | [11 empty] | 2018
Lead | Key Activity | >Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Inception (Evidence Gathering & Commnity Engagement)
AirS/SG | SG start up and formation | bar: 2016 >Dec
SG | NDP Launch and open day | bar: 2016 >Dec
SG/AirS | Focus Groups set up | bar: 2016 >Dec to 2017 Feb
SG/AirS | Ongoing engagement & evidence gathering | bar: 2017 Jan to 2017 Jun
SG/AirS | Survey work (NDP, Housing Needs) | bar: 2017 Feb to 2017 Jul
FGs | Engage with Businesses, YP, Organisations | bar: 2017 Feb to 2017 Jul
NP/FG | Review VDS and amend | bar: 2017 Jan to 2017 May
NP/JB | Idenity Heritage and Community Assets | bar: 2017 Mar to 2017 May
AirS/JB | Scoping Report Consultation | bar: 2017 Mar to 2017 May
LE FG | Carry out a Tourism survey | bar: 2017 Mar to 2017 May
JB/PC | Engage with landowners (call for sites) | bar: 2017 Mar to 2017 May
AirS/FG | Assess sites and write report | bar: 2017 May to 2017 Aug
Env FG | Identify and Allocate Local green Spaces | bar: 2017 Jun to 2017 Aug
Draft Plan & Regulation 14
AirS | Prepare draft plan and draft SEA | bar: 2017 Aug to 2017 sep
PC/SG | Carry out Regulation 14 | bar: 2017 sep to 2017 Oct
JB/AirS | Log and comment on representations | bar: 2017 Oct to 2017 Nov
AirS/SG | Meet with LPA | bar: 2017 Nov
AirS/SG | Finalise Consultation Statement | bar: 2017 Nov
Submission Plan & Regulatin 16
AirS | Amend plan and SEA with comments | bar: 2017 Nov to 2018 Jan
AirS | Write Basic Conditions Statement | bar: 2017 Nov to 2018 Jan
SG | SG approve, submit plan and associated documents to PC | bar: 2018 Jan to 2018 Feb
PC | PC submit plan and associated docs to LPA | bar: 2018 Jan to 2018 Feb
| SG - steering group | 2016 >Dec: PC - Parish Council; 2017 Jul: LPA - Local Planning Authority
| YP - Young People | 2016 >Dec: VDS - Village Design Statement