## General SG
Action in rural Sussex Project Guidance/Monitoring for West Wittering Neighbourhood Plan
Version 3 (June 2017)
Ref | Task in Detail | Task Group/ Lead | % Completion | Action
TASKS COMPLETE
C1 | SWOT Analysis | BH | 90% | Will be finalised to go into draft plan
C2 | Village Lifestyle Analysis | KM, BH, RL | 80% | To be finalised to feed into contextual evidence
C3 | Stakeholder Letters | JB | 90% | Recored all letters sent,- no further action
C4 | Focus Group Leaders Identified | NP.AT.RS.WB | 100% | Completed
C5
TASKS IN PROGRESS
P1 | Focus Groups Reports | NP.AT.RS.WB |  | Monthly Progress Update (FB to provide FG report template)
P2 | Scoping Report (consultation) | AirS/SG | 50% | Comments received. To be updated with comments and outcome of HNA then sent to SG for comments.
P3 | Contextual Evicence Report | SG/AirS | 50% | Pending. Ongoing working document, to be updated
P4 | Review Design Statement & Character Assessment (VDS) | NP/FG/ JB | 50% | CDC has passed on to their conservation team. Awaiting feedback. JB to send to CD Conservance for their input.
P5 | Identify Parish Heritage, Assets & Treasures | NP/JB | 30% | Data and Information being collected
P6 | Undertake Call for Sites | SG/JB | 50% | Call for sites carried out. Sites responded. FB to prepare site assessment template for Housing FG
P7 | Invite additional Questionnaires | SG/Airs | 5% | Decide if required or not (best done after HNA and completed Focus Group reports with recommendations
P8 | Tourism Survey (local businesses) | LE Group/ RS | 0% | Agree and action group. who? When? What questions?
P9
TASKS TO START
S1 | Identify potential Local Green Spaces | Env FG |  | Identifying sites to be designted as LGS in the NDP
S2 | Gather evidence for flooding and drainage issues | Env FG
S3 | Undertake a Housing Needs Assessment | JB/FB |  | Contact Locality to commission AECOM for a HNA
S4 | Biodiversity Conservation Designations Study | Env FG/ VDS
S5 | Assess sites and write report | AirS / Housing Group
S6 | Prepare Draft Policies | AirS |  | Based on outocme of FG Findings/outcome
S7 | Review and comment on Draft Plan | SG
S8