## General SG
Action in rural Sussex Project Guidance/Monitoring for West Wittering Neighbourhood Plan
Version 5 (October 2017)
Ref | Task in Detail | Task Group/ Lead | % Completion | Action
TASKS COMPLETE
C1 | SWOT Analysis | BH | 90% | Will be finalised to go into draft plan
C2 | Village Lifestyle Analysis | KM, BH, RL | 80% | To be finalised to feed into contextual evidence
C3 | Stakeholder Letters | JB | 90% | Recored all letters sent,- no further action
C4 | Focus Group Leaders Identified | NP.AT.RS.WB | 100% | Completed
C5 | Undertake Call for Sites | SG/JB | 95%
C6 | Invite additional Questionnaires | SG/Airs | 95%
TASKS IN PROGRESS
P1 | Focus Groups Reports | NP.AT.RS.WB |  | To produce draft reports by 15th Dec - to feed into draft plan
P2 | Scoping Report (consultation) | AirS/SG | 60% | To be worked into draft SA/SEA for steering group comments
P3 | Contextual Evicence Report | SG/AirS | 50% | Pending. Ongoing working document, to be updated
P4 | Review Design Statement & Character Assessment (VDS) | NP/FG/ JB | 50% | To go to parish council for approval. It will be developed concurrent with NDP and cnsulted on at same time.
P5 | Identify Heritage, Assets & Treasures | NP/JB | 30% | Data and Information being collected, workshop for Dec
P6 | Tourism Survey (local businesses) | LE Group/ RS | 80% | Agree and action group. who? When? What questions?
P7 | Undertake a Housing Needs Assessment | JB/FB | 10% | Feendcak to be sent to AECOM to commence study
P8 | Assess sites and write report | AirS / H FG | 35% | Housing profiles being compiled by Housing Group, to compile same profiles for all WW sites in CDC SHELAA
P9 | Gather evidence for flooding and drainage issues |  |  | PC carrying out a Flood Risk Mapping Project - this will support work of Env and Housing focus groups.
TASKS TO START
S1 | Identify potential Local Green Spaces | Env FG |  | Identifying sites to be designted as LGS in the NDP
S2 | Biodiversity Conservation Designations Study | Env FG/ VDS/JB |  | contact Sussex Bioviversity record centre with list/map of all sites to produce bespoke report around these sites.
S3 | Prepare Draft Policies | AirS |  | Based on outocme of FG Findings/outcome
S4
S5